## Sheet1
Can start? | Card No | As a | I want to | So that | Estimate | 2* Dev | 1*Code Review | 1* QA
Yes | 1 | Developer | have a website for Customer | I can develop customer facing features | 3 | Maria Latha | Claudia | Subha
Yes | 2 | Developer | have a website for Admin | I can develop administer facing features | 3 | Kanna Punitha | Maria | Jack
Yes | 3 | Developer | have a web service | I can develop web service features | 2 | Ajay Sarath | Kanna | Mike
Yes | 4 | Developer | have a data base | I can store data | 3 | James Mike | Jack | Latha
Maybe | 5 | Developer | connect to webservice from customer site | the customer site can consume the web service | 2 | Claudia Maria | Punitha | Ajay
Maybe | 6 | Developer | connect to webservice from admin site | the admin site can consume the web service | 2 | Subha Punitha | Sarath | James
Yes | 7 | Developer | Connect to the database from the web service | I can persist information about users and their blogs | 2 | Jack Kanna | Subha | Sarath
| 8 | Customer | Log into the web site | I can do what I'm allowed to do on the website | 3
| 9 | Customer | See blog posts | I can read them | 3
| 10 | Customer | Post a blog | I can upload content | 3
| 11 | Customer | Edit my own blogs | I can change erroneous content | 3
| 12 | Customer | Navigate the blogs | I can see a list of blog posts and navigate to them | 3
| 13 | Customer | See the comments on a blog post | I can see what people are saying about my blogs | 8
| 14 | Customer | Post a comment | I can respond to blog content | 5
| 15 | Customer | Log out from the web site | I can protect my account | 3
| 16 | Admin | Disable accounts | I can disable unwanted users | 5
| 17 | Customer | Register | I can use the website | 3
| 18 | Admin | Log into the admin website | I can do what I'm allowed to do on the website | 2
| 19 | Admin | Log out from the admin website | I can protect my account | 3
| 20 | Admin | Reset customer passwords | I can allow customers to log in again when they've forgotten their credentials | 1
| 21 | Admin | Disable blogs | I can stop unwanted blogs and their comments being displayed | 5
| 22 | Admin | Create another admin | I can share my workload | 3
| 23 | Admin | Change my password | I can keep my account secure | 1
Yes | 24 | Nuget |  |  |  | James | Mike | Latha